# EXECUTED SUBCONTRACT AGREEMENT

Structural Steel Fabrication & Erection
Seaport Civic Center
Issued by Northbridge Construction Group
Execution Date: 22 Jul 2026

| Document No. | SSA-STR-001 |
| --- | --- |
| Revision | 0 |
| Status | Executed |
| Reviewed By | Commercial Manager |
| Approved By | Director of Construction |

# Project Overview

Northbridge Construction Group has engaged Apex Structural Steel Ltd. to furnish, fabricate, deliver and erect the complete structural steel frame for the Seaport Civic Center. This subcontract forms part of the Main Works Contract and governs all structural steel activities.

# Project Team

| Discipline | Lead |
| --- | --- |
| Structural Design & Modeling | Safe Harbor Engineering, PC |
| Project Management & Architectural Modeling | Cartesian Inverse, PA |
| Architectural Design | Etienne Oiseau, LLC |
| Main Contractor | Northbridge Construction Group |

# Scope of Work

Prepare fabrication models and shop drawings.

Fabricate and supply structural steel.

Deliver steel in accordance with programme.

Erect frame, complete bolted and welded connections.

Provide QA records, as-builts and closeout.

# Commercial Summary

Contract Value: USD $3,850,000

Retention: 5%

Payment Terms: Net 30

Warranty: 12 months

# Quality, Safety & Digital Delivery

Work shall comply with project specifications and applicable codes.

Weekly coordination meetings are mandatory.

RFIs, Submittals, Issues and Documents managed in Autodesk Construction Cloud.

Native Revit structural model is the contractual coordination model.

# Programme & Milestones

| Milestone | Target Date |
| --- | --- |
| Shop Drawings Approved | 22 Jul 2026 |
| Fabrication Complete | 26 Aug 2026 |
| Steel Delivery | 9 Sep 2026 |
| Steel Erection Begins | 16 Sep 2026 |
| Structural Frame Complete | 25 Nov 2026 |

# Schedule of Values

| Package | % | USD |
| --- | --- | --- |
| Shop Drawings | 5 | 192,500 |
| Fabrication | 45 | 1,732,500 |
| Delivery | 10 | 385,000 |
| Erection | 35 | 1,347,500 |
| Closeout | 5 | 192,500 |

# Reference Documents

Structural Steel Specification – Section 05 12 00

Inspection and Test Plan (ITP) – Structural Steel Works

Project Health, Safety & Environmental Management Plan

Construction Programme – Rev A

# Execution

Main Contractor Representative
Name: ______________________
Signature: ______________________

Subcontractor Representative
Name: ______________________
Signature: ______________________

# Document Control

| Item | Value |
| --- | --- |
| Document No. | SSA-STR-001 |
| Revision | 0 |
| Status | Executed |
| Prepared By | Jonathan Hand, Technical Marketing Manager |
| Reviewed By | Commercial Manager |
| Approved By | Director of Construction |