## Overview
Sample Project
Issue summary
Issue summary
Created on
Created by | Jonathan Hand (Apex Program Management)
Total items | 289
Sorted by | ID (Descending)

## Issues
ID | Title | Status | Category | Type | Description | Assigned to | Company | Watchers | Created by | Created on | Due date | Start date | Location | Location details | Placement | Root cause | Published | Updated by | Updated on | Closed by | Closed at | Comments | Additional Comments | Areas Affected | Building Element | Cost Impact? | Date Received | Defect | Did you Link an Asset? - You should link an asset | Facilities Team Review Status | Hyperlink | Hyperlink | Install Date | Interface Topic | Lessons Learned Candidate? | Multi-select dropdown | Numeric | Part Number | Project Task Code | Quality Issue with Cost | Review Status | Risk Level | Row | SC Acknowledged | Seat | Serial Number | Serial Number | Ship Date | Size | Warranty Info | Warranty Number | Work Order #
#1873 | Punch List | Open | Punch List | Punch List |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-08-03 16:56 | [6 empty] | Published |  | 2026-08-03 16:56
#1872 | COI | Open | Admin Insurance | COI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-08-03 12:50 | [6 empty] | Published |  | 2026-08-03 12:50
#1871 | Design | Pending | Design | Design |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-07-29 10:39 |  |  | 05 ROOF |  |  |  | Published |  | 2026-08-03 09:36
#1870 | Owner T&M Directive | Open | Change Management | Owner T&M Directive |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-07-28 11:15 | [6 empty] | Published |  | 2026-07-31 08:08
#1869 | COI | Open | Admin Insurance | COI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-07-27 07:57 | [6 empty] | Published |  | 2026-07-27 07:57
#1868 | Admin Insurance | Open | Admin Insurance | COI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-07-27 07:55 | [6 empty] | Published |  | 2026-07-27 07:55
#1867 | Med Issue Test | Draft | Change Management | Internal T&M |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-07-27 07:54 | [6 empty] | Published |  | 2026-07-27 07:54
#1866 | Small Works Handoff Template | Draft | Commissioning | Small Works Handoff |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-07-27 07:38 | 2026-08-01 |  | 00 FIRST - FINISH FLOOR |  |  |  | Published |  | 2026-07-27 07:39
#1865 | Small Works Handoff Template | Draft | Commissioning | Small Works Handoff |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-07-27 07:38 | 2026-08-01 |  | 00 FIRST - FINISH FLOOR |  |  |  | Published |  | 2026-07-27 07:38
#1863 | Basic Wall [1073527] and Pipe Types [3753158] | Open | Coordination | Clash | 1 clash between Basic Wall [1073527] in R21 LTU Housing - Struc.rvt - STRUC - PHYSICAL MODEL and R21 LTU Housing - PLUMBING.rvt - MEP - COORDINATION | Autodesk | Autodesk | Autodesk | Autodesk | 2026-07-24 15:36 | [6 empty] | Published |  | 2026-07-24 15:36
#1862 | Commissioning | Open | Commissioning | Commissioning |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-07-22 12:34 | 2026-07-29 | [5 empty] | Published |  | 2026-07-22 12:34
#1861 | Hole in Wall Near Window | Open | Change Management | Internal T&M | There is a hole present in the wall below the window, indicating damage that requires patching and repair to restore the wall surface. | Autodesk | Autodesk | Autodesk | Autodesk | 2026-07-21 13:28 | [5 empty] | Construction Defects | Published |  | 2026-07-21 13:28 |  |  |  | Wall damage is visible below the window and should be repaired to maintain finish quality.
#1860 | Hole in Wall Below Window | Draft | Change Management | Internal T&M | There is a visible hole in the wall beneath the window, likely caused by poor craftsmanship or accidental damage during construction or installation. | Autodesk | Autodesk | Autodesk | Autodesk | 2026-07-21 13:26 | [5 empty] | Poor Craftsmanship | Published |  | 2026-07-21 13:26 |  |  |  | Repair the hole in the wall and restore the surface to match the surrounding finish.
#1859 | Subcontractor T&M | Draft | Change Management | Subcontractor T&M |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-07-21 07:40 | [6 empty] | Published |  | 2026-07-21 07:41
#1858 | CO2 | Open | Admin Insurance | COI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-07-16 12:57 | [6 empty] | Published |  | 2026-07-16 12:58
#1857 | COI | Open | Admin Insurance | COI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-07-16 12:54 | [6 empty] | Published |  | 2026-07-16 12:54
#1856 | Punch List | Open | Punch List | Punch List |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-07-16 12:38 | [6 empty] | Published |  | 2026-07-16 12:38
#1854 | COI | Open | Admin Insurance | COI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-07-16 00:01 | [6 empty] | Published |  | 2026-07-16 00:01
#1853 | Image is too dark to assess construction issue | Open | Punch List | Punch List | The provided image is completely dark, preventing identification or analysis of any construction defects or issues. A clearer photo or additional context is required for proper assessment. | Autodesk | Autodesk | Autodesk | Autodesk | 2026-07-15 20:14 |  |  | 03 THIRD - FINISH FLOOR > E-330 |  |  |  | Published |  | 2026-07-15 20:14 |  |  |  |  | Quality | [16 empty] | Incomplete
#1852 | Unusable Photo for Construction Issue Documentation | Open | Punch List | Punch List | The provided image is out of focus and does not show any identifiable construction defect or issue, preventing proper assessment or documentation. | Autodesk | Autodesk | Autodesk | Autodesk | 2026-07-15 20:13 | [5 empty] | Communication | Published |  | 2026-07-15 20:14 |  |  |  |  | Quality | [16 empty] | Incomplete
#1851 | Incorrect Carpet Tile Installation | Open | Punch List | Punch List | A carpet tile is installed incorrectly, resulting in misalignment with the surrounding pattern and visible discrepancy in the floor finish. | Autodesk | Autodesk | Autodesk | Autodesk | 2026-07-15 19:50 | [5 empty] | Poor Craftsmanship | Published |  | 2026-07-15 19:52 |  |  |  |  | Quality
#1850 | Quality | Open | Concrete Crew | Quality |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-07-15 15:42 | [6 empty] | Published |  | 2026-07-15 20:13
#1849 | COI | Open | Admin Insurance | COI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-07-14 15:50 | [6 empty] | Published |  | 2026-07-14 15:50
#1848 | Subcontractor T&M | Draft | Change Management | Subcontractor T&M |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-07-09 11:29 | [6 empty] | Published |  | 2026-07-14 09:17
#1847 | Quality | Open | Concrete Crew | Quality |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-07-02 13:21 | [6 empty] | Published |  | 2026-07-02 13:21
#1846 | EPC 30 Review | Draft | EPC Engineering Review | 30 Review |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-06-29 13:01 | 2026-07-02 | [5 empty] | Published |  | 2026-06-29 13:06 |  |  | Matt Bunis (Jun 29, 2026, 1:06 PM PDT): @Miguel Coronel need you to take a look at this one | [16 empty] | deijubwcuih
#1845 | Unclear or Obstructed Photo Provided | Open | Punch List | Punch List | The submitted image is out of focus or obstructed, preventing assessment of any construction issue. A clear and relevant photo is required for proper documentation and resolution. | Autodesk | Autodesk | Autodesk | Autodesk | 2026-06-28 04:40 | [5 empty] | Bad Site Survey | Published |  | 2026-06-28 04:40 |  |  |  | Image quality prevents identification of construction issues; retake with clear focus. | Quality | [16 empty] | Incomplete
#1844 | Design | Open | Design | Design |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-06-16 11:47 | [6 empty] | Published |  | 2026-06-16 11:47
#1843 | RFI | Open | Commissioning | RFI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-06-12 15:14 |  |  | 04 FOURTH - FINISH FLOOR > W-421 |  |  |  | Published |  | 2026-06-22 07:49
#1842 | COI | Open | Admin Insurance | COI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-06-09 05:53 | [6 empty] | Published |  | 2026-06-24 12:39
#1841 | Internal T&M | Draft | Change Management | Internal T&M |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-06-09 05:52 | [6 empty] | Published |  | 2026-06-09 05:52
#1840 | COI | Open | Admin Insurance | COI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-06-09 04:53 | [6 empty] | Published |  | 2026-06-09 06:05
#1839 | EPC 30 Review | Open | EPC Engineering Review | 30 Review |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-06-08 10:29 | 2026-06-11 | [5 empty] | Published |  | 2026-06-08 10:31 |  |  | Matt Bunis (Jun 8, 2026, 10:30 AM PDT): @Miguel Coronel hey need your opinion on this one | [16 empty] | 12a4f5ad
#1838 | Punch List | Open | Punch List | Punch List |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-06-03 06:18 | [6 empty] | Published |  | 2026-06-03 06:18
#1837 | EPC 30 Review | Draft | EPC Engineering Review | 30 Review |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-06-02 11:54 | 2026-06-05 | [5 empty] | Published |  | 2026-06-02 11:55 | [19 empty] | 1278124678512
#1836 | Paint TouchUp | Draft | Punch List | Architectural Punch List | paint touch up | Autodesk | Autodesk | Autodesk | Autodesk | 2026-05-29 10:06 | [5 empty] | Construction Defects | Published |  | 2026-05-29 10:07
#1835 | Design | Open | Design | Design |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-05-28 13:02 | [6 empty] | Published |  | 2026-05-28 13:02
#1831 | COI | Open | Life Safety - Design | Life Safety - Design |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-05-26 13:45 | [6 empty] | Published |  | 2026-07-28 16:56
#1830 | Architect to modify drawings | Open | Admin Insurance | COI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-05-26 09:45 | [6 empty] | Published |  | 2026-05-26 09:45
#1829 | Mechanical Design Conflict | Draft | Concrete Crew | Design Conflict |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-05-22 09:30 | 2026-06-01 |  |  |  |  | Design Coordination | Published |  | 2026-05-22 09:30
#1826 | Design Conflict | Draft | Concrete Crew | Design Conflict |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-05-21 09:10 | [6 empty] | Published |  | 2026-05-21 09:10
#1825 | Architectural Punch List | Draft | Punch List | Architectural Punch List |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-05-18 11:21 | 2026-05-21 | [5 empty] | Published |  | 2026-05-18 11:21
#1822 | CM TC WSHP and Disconnect Switches [3902591] | Open | Commissioning | RFI | 1 clash between CM TC WSHP in R21 LTU Housing - MEP_luke.hesterME9FZ.rvt - 3D View 3 and ADSK_Mechanical.rvt - COORD - MEP-ALL | Autodesk | Autodesk | Autodesk | Autodesk | 2026-05-14 11:41 | [6 empty] | Published |  | 2026-05-14 11:42
#1821 | Owner T&M Directive | Open | Change Management | Owner T&M Directive |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-05-14 11:13 |  |  | 00 FIRST - FINISH FLOOR > E-102 |  |  |  | Published |  | 2026-05-14 11:13
#1819 | Trash left on conference table | Closed | Punch List | Punch List | Food wrappers, cups, and paper scraps have been left on the conference table, indicating poor housekeeping and lack of cleanliness. | Autodesk | Autodesk | Autodesk | Autodesk | 2026-05-14 10:34 | [5 empty] | Housekeeping | Published |  | 2026-07-15 01:56 | Yaara Haneman | 2026-07-15 08:56 |  |  | Quality
#1817 | Paint TouchUp | Draft | Punch List | Architectural Punch List | paint touch up | Autodesk | Autodesk | Autodesk | Autodesk | 2026-05-14 10:32 | [5 empty] | Construction Defects | Published |  | 2026-05-14 10:32
#1816 | Commissioning | Open | Commissioning | Commissioning |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-05-14 10:22 | [6 empty] | Published |  | 2026-05-14 10:22
#1815 | EPC 30 Review | Draft | EPC Engineering Review | 30 Review |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-05-14 10:11 | 2026-05-17 | [5 empty] | Published |  | 2026-07-27 10:53
#1814 | QA/QC Safety Issue Template | Open | Quality | Quality | Please use this Template for capturing QA/QC Issues. | Autodesk | Autodesk | Autodesk | Autodesk | 2026-05-14 09:32 | [6 empty] | Published |  | 2026-05-14 09:32
#1813 | Wall Type not Comliant | Open | Due Diligence | Due Diligence Flag |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-05-14 07:37 | 2026-05-20 | [5 empty] | Published |  | 2026-05-14 07:41 |  |  | Ali Atabey (May 14, 2026, 7:40 AM PDT): @Adam Luttenbacher please share spec details for compliance
#1812 | Punch List | Open | Punch List | Punch List |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-05-12 08:18 |  |  | 00 FIRST - FINISH FLOOR |  |  |  | Published |  | 2026-05-12 08:18
#1810 | Ventilation Grille Obstructed by Cabinet Installation | Open | Punch List | Punch List | The cabinet is installed directly in front of the ventilation grille, restricting airflow and compromising HVAC performance. This placement may lead to inadequate ventilation and potential code compliance issues. | Autodesk | Autodesk | Autodesk | Autodesk | 2026-05-05 12:53 | 2026-05-22 |  |  |  |  | Constructability | Published |  | 2026-05-05 13:18 |  |  |  |  | Quality
#1809 | Windows LEED eligibility | Open | Design | Design | Windows as specified are insufficient for 3 points in this climate zone | Autodesk | Autodesk | Autodesk | Autodesk | 2026-05-05 11:41 | [6 empty] | Published |  | 2026-05-05 11:41
#1808 | Architectural Punch List | Draft | Punch List | Architectural Punch List |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-05-04 12:50 | 2026-05-07 | [5 empty] | Published |  | 2026-05-21 10:59 |  |  | Matt Bunis (May 4, 2026, 12:51 PM PDT): @Miguel Coronel need your thoughts on this
#1807 | Safety infraction | Open | Safety | Safety Infraction | Window trim out of alignment | Autodesk | Autodesk | Autodesk | Autodesk | 2026-05-01 08:54 | 2026-05-04 | [5 empty] | Published |  | 2026-05-01 08:56
#1806 | Commissioning | Pending | Commissioning | Commissioning |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-04-30 12:42 | [6 empty] | Published |  | 2026-05-05 14:12
#1804 | Mechanical QA Issue Template | Draft | Commissioning | Mechanical Equipment CX |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-04-29 10:55 | [6 empty] | Published |  | 2026-04-29 10:55 | [9 empty] | YES
#1803 | Small Works Handoff Template | Draft | Commissioning | Small Works Handoff |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-04-29 10:36 | 2026-05-04 | [5 empty] | Published |  | 2026-04-29 10:36
#1800 | COI | Open | Admin Insurance | COI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-04-28 13:41 |  |  | 04 FOURTH - FINISH FLOOR > W-421 |  |  |  | Published |  | 2026-04-29 10:39
#1799 | COI | Open | Admin Insurance | COI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-04-27 11:08 | [6 empty] | Published |  | 2026-04-27 11:08
#1798 | Punch List - Flooring Tile | Open | Punch List | Architectural Punch List | This is the template text | Autodesk | Autodesk | Autodesk | Autodesk | 2026-04-22 11:13 | 2026-04-25 |  | 04 FOURTH - FINISH FLOOR > W-418 | SW Corner |  | Poor Craftsmanship | Published |  | 2026-04-22 11:13 |  |  |  |  | Quality
#1797 | EPC 30 Review | Draft | EPC Engineering Review | 30 Review |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-04-21 09:25 | 2026-04-24 | [5 empty] | Published |  | 2026-04-21 09:25
#1795 | Mechanical QA Issue Template | Draft | Commissioning | Mechanical Equipment CX |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-04-16 11:26 | 2026-04-23 | [5 empty] | Published |  | 2026-04-20 02:52 | [9 empty] | YES | [20 empty] | 456 | 123
#1794 | Mechanical QA Issue Template | Closed | Commissioning | Mechanical Equipment CX | TEST | Autodesk | Autodesk | Autodesk | Autodesk | 2026-04-16 10:20 | 2026-04-23 | [5 empty] | Published |  | 2026-04-23 12:25 | Luke Hester ACS-TSE-Construction | 2026-04-23 19:25 | [7 empty] | NO | [20 empty] | 456 | 123
#1793 | Ceiling damage | Open | Observation | Observation | Plumbing leaks | Autodesk | Autodesk | Autodesk | Autodesk | 2026-04-15 13:33 | 2026-05-22 |  |  |  |  | Wear and Tear | Published |  | 2026-05-05 13:19
#1792 | Ceiling damage | Open | Observation | Observation | Water stains around light fixture | Autodesk | Autodesk | Autodesk | Autodesk | 2026-04-15 13:31 | 2026-05-22 |  |  |  |  | Wear and Tear | Published |  | 2026-05-05 13:19 |  |  | Cheryle Cranbourne (Apr 15, 2026, 1:32 PM PDT): Check roof/ seal around roof equipment above
#1791 | FCU Issue | Open | Observation | Observation |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-04-15 13:25 | 2026-05-22 |  | 04 FOURTH - FINISH FLOOR |  |  | Wear and Tear | Published |  | 2026-05-05 13:20
#1785 | COI | Open | Admin Insurance | COI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-04-15 12:28 | 2026-04-20 | [5 empty] | Published |  | 2026-06-09 04:46
#1784 | COI | Open | Admin Insurance | COI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-04-15 12:26 | 2026-04-20 | [5 empty] | Published |  | 2026-04-17 05:27
#1783 | COI | Open | Admin Insurance | COI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-04-15 12:26 | 2026-04-20 | [5 empty] | Published |  | 2026-04-17 05:27
#1782 | COI | Open | Admin Insurance | COI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-04-15 12:26 | 2026-04-20 | [5 empty] | Published |  | 2026-04-17 05:27
#1781 | COI | Open | Admin Insurance | COI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-04-15 12:26 | 2026-04-20 | [5 empty] | Published |  | 2026-04-17 05:27
#1780 | COI | Open | Admin Insurance | COI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-04-15 12:26 | 2026-04-20 | [5 empty] | Published |  | 2026-04-17 05:27
#1779 | COI | Open | Admin Insurance | COI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-04-15 12:26 | 2026-04-20 | [5 empty] | Published |  | 2026-04-17 05:27
#1778 | COI | Open | Admin Insurance | COI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-04-15 12:26 | 2026-04-20 | [5 empty] | Published |  | 2026-06-09 06:19
#1776 | Ceiling Fan Installed Too Close to Fire Sprinkler Head | Open | Punch List | Punch List | Ceiling fan placement is too close to the fire sprinkler head, potentially obstructing sprinkler coverage and violating fire safety codes. | Autodesk | Autodesk | Autodesk | Autodesk | 2026-04-15 11:45 | 2026-04-23 |  |  |  |  | Code Compliance | Published |  | 2026-04-20 02:52 |  |  |  |  | Safety
#1769 | Mechanical Equipment CX | Draft | Commissioning | Mechanical Equipment CX |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-04-14 09:06 | 2026-04-23 | [5 empty] | Published |  | 2026-04-20 02:52
#1768 | Owners Issues | Open | Design | Design |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-04-13 11:34 | 2026-04-12 | [5 empty] | Published |  | 2026-04-13 11:34
#1767 | Owners Issues | Open | Design | Design |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-04-13 11:34 | 2026-04-12 | [5 empty] | Published |  | 2026-04-13 11:34
#1766 | COI | Open | Admin Insurance | COI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-04-07 16:24 | 2026-04-20 | [5 empty] | Published |  | 2026-04-17 05:27
#1765 | VAV Issue | Open | Design | Design |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-04-07 10:49 | 2026-04-12 | [5 empty] | Published |  | 2026-04-15 13:17
#1763 | Subcontractor T&M | Draft | Change Management | Subcontractor T&M | Look above the ceiling capture photo | Autodesk | Autodesk | Autodesk | Autodesk | 2026-03-30 15:45 | 2026-04-23 | [5 empty] | Published |  | 2026-04-20 02:52
#1762 | Swing Direction | Open | Concrete Crew | Finish |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-03-27 05:17 | 2026-04-23 | [5 empty] | Published |  | 2026-04-20 02:52
#1761 | COI | Open | Admin Insurance | COI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-03-26 11:31 | 2026-04-20 | [5 empty] | Published |  | 2026-04-17 05:27
#1759 | COI | Completed | Concrete Crew | Safety |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-03-26 11:27 | 2026-01-15 | 2026-02-09 |  |  |  | Human - Human error | Published |  | 2026-03-26 11:28
#1758 | Loose Cable Creating Tripping Hazard | Open | Punch List | Punch List | An unsecured cable is running across the walking area, presenting a tripping hazard and potential safety risk. | Autodesk | Autodesk | Autodesk | Autodesk | 2026-03-12 10:09 | 2026-04-23 |  |  |  |  | Human - Failed to identify unsafe condition | Published |  | 2026-04-20 02:52 |  |  |  |  | Safety
#1757 | Design Conflict | Draft | Concrete Crew | Design Conflict |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-03-11 06:36 | 2026-04-23 | [5 empty] | Published |  | 2026-04-20 02:52 |  |  | Matt Bunis (Mar 11, 2026, 6:36 AM PDT): i think this needs to be elevated to an RFI
#1756 | Architectural Punch List | Draft | Punch List | Architectural Punch List |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-03-10 12:46 | 2026-04-20 | [5 empty] | Published |  | 2026-04-17 05:27 |  |  | Matt Bunis (Mar 10, 2026, 12:48 PM PDT): @Miguel Coronel i need you to look at this ASAP
#1755 | Client Feedback | Open | Design | Client Feedback |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-02-27 06:41 | 2026-04-20 | [5 empty] | Published |  | 2026-04-17 05:27
#1753 | Design-Detail | Open | Design | Design | Check detail | Autodesk | Autodesk | Autodesk | Autodesk | 2026-02-24 06:45 | 2026-04-23 | [5 empty] | Published |  | 2026-04-20 02:52
#1752 | Building Code - ADA | Open | Design | Building Code |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-02-18 08:08 | 2026-04-20 | [5 empty] | Published |  | 2026-04-17 05:27
#1751 | housekeeping, access, egress, welding, cutting, sharp edges, excavation, power tools, | Open | Safety | Safety Infraction | housekeeping, access, egress, welding, cutting, sharp edges, excavation, power tools, hand tools, etc. | Autodesk | Autodesk | Autodesk | Autodesk | 2026-02-17 04:37 | 2026-01-15 | 2026-02-20 | 04 FOURTH - FINISH FLOOR > E-430 | Base of Column G14 |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:38
#1750 | housekeeping, access, egress, welding, cutting, sharp edges, excavation, power tools, | Open | Safety | Safety Infraction | housekeeping, access, egress, welding, cutting, sharp edges, excavation, power tools, hand tools, etc. | Autodesk | Autodesk | Autodesk | Autodesk | 2026-02-17 04:28 | 2026-01-15 |  | 00 BASEMENT > Parking Level 1 |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:38
#1749 | Punch List | Open | Punch List | Punch List |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-02-17 04:11 | 2026-04-23 | [5 empty] | Published |  | 2026-04-20 02:52
#1748 | Toolbox Meeting Issue | Open | Safety | Toolbox Meeting |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-02-17 03:50 | 2026-02-12 | 2026-02-11 |  |  |  | Management - Lack of protective safety equipment | Published |  | 2026-02-17 03:50
#1747 | housekeeping, access, egress, welding, cutting, sharp edges, excavation, power tools, | Completed | Safety | Safety Infraction | housekeeping, access, egress, welding, cutting, sharp edges, excavation, power tools, hand tools, etc. | Autodesk | Autodesk | Autodesk | Autodesk | 2026-02-17 03:50 | 2026-02-13 | 2026-02-09 |  |  |  | Human - Lack of coordination | Published |  | 2026-05-13 02:41
#1746 | Small Works Handoff Template | Draft | Safety | Safety Infraction |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-02-13 12:08 | 2026-02-13 | 2026-02-09 |  |  |  | Human - Human error | Published |  | 2026-02-17 03:55
#1745 | housekeeping, access, egress, welding, cutting, sharp edges, excavation, power tools, | Open | Safety | Safety Infraction | housekeeping, access, egress, welding, cutting, sharp edges, excavation, power tools, hand tools, etc. | Autodesk | Autodesk | Autodesk | Autodesk | 2026-02-13 07:32 | 2026-02-13 | 2026-02-09 |  |  |  | Human - Human error | Published |  | 2026-02-19 02:38
#1744 | housekeeping, access, egress, welding, cutting, sharp edges, excavation, power tools, | Open | Safety | Safety Infraction | housekeeping, access, egress, welding, cutting, sharp edges, excavation, power tools, hand tools, etc. | Autodesk | Autodesk | Autodesk | Autodesk | 2026-02-11 15:08 | 2026-02-13 | 2026-02-09 |  |  |  | Human - Human error | Published |  | 2026-02-19 02:38
#1743 | housekeeping, access, egress, welding, cutting, sharp edges, excavation, power tools, | Open | Safety | Safety Infraction | housekeeping, access, egress, welding, cutting, sharp edges, excavation, power tools, hand tools, etc. | Autodesk | Autodesk | Autodesk | Autodesk | 2026-02-10 22:23 | 2026-02-13 | 2026-02-09 |  |  |  | Human - Human error | Published |  | 2026-02-19 02:38
#1741 | housekeeping, access, egress, welding, cutting, sharp edges, excavation, power tools, | Open | Safety | Safety Infraction | housekeeping, access, egress, welding, cutting, sharp edges, excavation, power tools, hand tools, etc. | Autodesk | Autodesk | Autodesk | Autodesk | 2026-02-05 12:13 | 2026-01-15 | 2026-02-09 |  |  |  | Human - Human error | Published |  | 2026-02-19 02:38
#1740 | Design Conflict | Draft | Safety | Safety Infraction |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-02-02 07:36 | 2026-01-15 | 2026-02-09 |  |  |  | Human - Human error | Published |  | 2026-02-19 02:24
#1738 | housekeeping, access, egress, welding, cutting, sharp edges, excavation, power tools, | Open | Safety | Safety Infraction | housekeeping, access, egress, welding, cutting, sharp edges, excavation, power tools, hand tools, etc. | Autodesk | Autodesk | Autodesk | Autodesk | 2026-01-23 03:43 | 2026-01-15 | 2026-02-09 |  |  |  | Human - Human error | Published |  | 2026-05-14 10:09
#1737 | housekeeping, access, egress, welding, cutting, sharp edges, excavation, power tools, | Open | Safety | Safety Infraction | housekeeping, access, egress, welding, cutting, sharp edges, excavation, power tools, hand tools, etc. | Autodesk | Autodesk | Autodesk | Autodesk | 2026-01-22 12:23 | 2026-01-15 | 2026-02-09 |  |  |  | Human - Human error | Published |  | 2026-02-19 02:38
#1735 | housekeeping, access, egress, welding, cutting, sharp edges, excavation, power tools, | Open | Safety | Safety Infraction | housekeeping, access, egress, welding, cutting, sharp edges, excavation, power tools, hand tools, etc. | Autodesk | Autodesk | Autodesk | Autodesk | 2026-01-21 12:57 | 2026-01-15 | 2026-02-09 |  |  |  | Human - Human error | Published |  | 2026-02-19 02:38
#1734 | housekeeping, access, egress, welding, cutting, sharp edges, excavation, power tools, | Open | Safety | Safety Infraction | housekeeping, access, egress, welding, cutting, sharp edges, excavation, power tools, hand tools, etc. | Autodesk | Autodesk | Autodesk | Autodesk | 2026-01-21 11:37 | 2026-01-15 | 2026-02-09 |  |  |  | Human - Human error | Published |  | 2026-02-19 02:38
#1733 | Quality | In dispute | Safety | Safety Infraction |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-01-21 10:30 | 2026-01-15 | 2026-02-09 |  |  |  | Human - Human error | Published |  | 2026-02-19 02:33
#1732 | Owner T&M Directive | In dispute | Safety | Safety Infraction |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-01-20 10:32 | 2026-01-15 | 2026-02-09 |  |  |  | Human - Human error | Published |  | 2026-02-19 02:33
#1731 | COI | In dispute | Safety | Safety Infraction |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-01-20 07:19 | 2026-01-15 | 2026-02-09 |  |  |  | Human - Human error | Published |  | 2026-02-19 02:33
#1729 | Observation | In dispute | Safety | Safety Infraction |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-01-14 15:35 | 2026-01-15 | 2026-02-09 |  |  |  | Human - Human error | Published |  | 2026-02-19 02:33
#1728 | Internal T&M | Not approved | Safety | Safety Infraction |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-01-09 11:47 | 2026-01-15 | 2026-02-09 |  |  |  | Human - Human error | Published |  | 2026-02-19 02:24
#1727 | COI | In dispute | Safety | Safety Infraction |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-01-09 11:16 | 2026-01-15 | 2026-02-09 | 00 FIRST - FINISH FLOOR |  |  | Human - Human error | Published |  | 2026-02-19 02:33
#1726 | Architectural Punch List | Pending | Safety | Safety Infraction |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-01-09 10:44 | 2026-01-15 | 2026-02-09 | 00 FIRST - FINISH FLOOR |  |  | Human - Human error | Published |  | 2026-02-19 02:24 |  |  | Matt Bunis (Jan 9, 2026, 10:44 AM PST): @matthew bunis need you to look at this ASAP
#1725 | Commissioning | In dispute | Safety | Safety Infraction |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-01-08 06:46 | 2026-01-15 | 2026-02-09 |  |  |  | Human - Human error | Published |  | 2026-02-19 02:33
#1724 | COI | Completed | Concrete Crew | Safety |  | Autodesk | Autodesk | Autodesk | Autodesk | 2026-01-07 11:40 | 2026-01-15 | 2026-02-09 |  |  |  | Human - Human error | Published |  | 2026-02-19 02:24
#1723 | COI | In dispute | Safety | Safety Infraction | Text | Autodesk | Autodesk | Autodesk | Autodesk | 2026-01-07 11:31 | 2026-01-15 | 2026-02-09 |  |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33
#1722 | COI | In dispute | Safety | Safety Infraction |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-12-19 09:50 | 2026-01-15 | 2026-02-09 |  |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33
#1720 | Commissioning | In review | Concrete Crew | Safety |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-12-16 08:50 | 2026-01-15 | 2026-02-09 |  |  |  | Human - Human error | Published |  | 2026-02-19 02:24
#1719 | COI | In dispute | Safety | Safety Infraction |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-12-15 12:27 | 2026-01-15 | 2026-02-09 |  |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33
#1718 | Package for Design | In review | Concrete Crew | Safety |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-12-15 11:41 | 2026-01-15 | 2026-02-09 |  |  |  | Human - Human error | Published |  | 2026-02-19 02:24
#1715 | COI | In dispute | Safety | Safety Infraction |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-12-12 13:26 | 2026-01-15 | 2026-02-09 |  |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33
#1714 | COI | Completed | Concrete Crew | Safety | Fire door | Autodesk | Autodesk | Autodesk | Autodesk | 2025-12-11 08:37 | 2026-01-15 | 2026-02-09 |  |  |  | Human - Human error | Published |  | 2026-07-10 08:06
#1713 | Quality | Pending | Concrete Crew | Safety |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-12-08 14:45 | 2026-07-16 | 2026-02-09 | 01 FIRST - FINISH FLOOR > E-104 |  |  | Human - Human error | Published |  | 2026-07-10 08:22
#1712 | Quality | In dispute | Safety | Safety Infraction |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-12-05 12:23 | 2027-01-14 | 2026-02-09 |  |  |  | Equipment - Improper equipment | Published |  | 2026-07-14 10:49
#1711 | Change Window Type | In progress | Concrete Crew | Safety |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-12-05 06:47 | 2026-01-15 | 2026-02-09 |  |  |  | Human - Human error | Published |  | 2026-02-19 02:24 |  |  | Ali Atabey (Dec 5, 2025, 6:48 AM PST): @Gabe Morales please provide spec sheet for the new window
#1710 | 30 Review | In dispute | Safety | Safety Infraction |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-12-03 06:55 | 2026-01-15 | 2026-02-09 |  |  |  | Equipment - Improper equipment | Published |  | 2026-07-10 11:26
#1709 | Quality | In dispute | Safety | Safety Infraction |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-12-02 13:18 | 2026-01-15 | 2026-02-09 |  |  |  | Equipment - Improper equipment | Published |  | 2026-07-10 08:04
#1707 | Architectural Punch List | In dispute | Safety | Safety Infraction | Door Damaged | Autodesk | Autodesk | Autodesk | Autodesk | 2025-11-25 12:36 | 2026-01-15 | 2026-02-09 | 01 FIRST - FINISH FLOOR > E-134 |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33
#1705 | Jackson Hole New Store | In dispute | Safety | Safety Infraction | looking to go skiing | Autodesk | Autodesk | Autodesk | Autodesk | 2025-11-19 13:21 | 2026-01-15 | 2026-02-09 |  |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33
#1704 | Project Intake | In dispute | Safety | Safety Infraction | slab needs upgrading | Autodesk | Autodesk | Autodesk | Autodesk | 2025-11-19 13:12 | 2026-01-15 | 2026-02-09 |  |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33
#1703 | Quality | In dispute | Safety | Safety Infraction |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-11-19 12:37 | 2026-01-15 | 2026-02-09 |  |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33
#1702 | Architectural Punch List | Draft | Concrete Crew | Safety | window damaged | Autodesk | Autodesk | Autodesk | Autodesk | 2025-11-19 12:33 | 2026-01-15 | 2026-02-09 | 01 FIRST - FINISH FLOOR > E-125 |  |  | Human - Human error | Published |  | 2026-02-19 02:24
#1701 | New Project Intake - Denver | In dispute | Safety | Safety Infraction | Looking to expand the Rocky Mountain market, and Matt lives here so he is partial to a new Nike store close to home | Autodesk | Autodesk | Autodesk | Autodesk | 2025-11-19 11:35 | 2026-01-15 | 2026-02-09 |  |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33
#1700 | New Project Intake - Dallas | In dispute | Safety | Safety Infraction | Looking to expand here ahead of 2028 Olympics | Autodesk | Autodesk | Autodesk | Autodesk | 2025-11-19 11:23 | 2026-01-15 | 2026-02-09 |  |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33
#1698 | Toolbox Meeting | Completed | Concrete Crew | Safety |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-11-12 10:32 |  | 2026-02-09 |  |  |  | Human - Human error | Published |  | 2026-07-14 10:52
#1697 | Installation Instructions | In progress | Concrete Crew | Safety |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-11-05 08:16 | 2026-01-15 | 2026-02-09 |  |  |  | Human - Human error | Published |  | 2026-02-19 02:24
#1696 | Owner T&M Directive | Completed | Concrete Crew | Safety | Move here | Autodesk | Autodesk | Autodesk | Autodesk | 2025-11-05 06:19 | 2026-01-15 | 2026-02-09 |  |  |  | Human - Human error | Published |  | 2026-02-19 02:24
#1695 | PO Received | In dispute | Safety | Safety Infraction |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-11-04 12:14 | 2026-01-15 | 2026-02-09 | 05 ROOF |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33
#1694 | Inspection | In dispute | Safety | Safety Infraction | Door is not closing. | Autodesk | Autodesk | Autodesk | Autodesk | 2025-11-03 09:12 | 2026-01-15 | 2026-02-09 | 01 FIRST - FINISH FLOOR > E-125 |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33 |  |  | Lisa Chen (Nov 3, 2025, 9:13 AM PST): @Tyler Camp
#1693 | Building Code | In dispute | Safety | Safety Infraction | Hazardous condition needs to fix | Autodesk | Autodesk | Autodesk | Autodesk | 2025-10-31 07:46 | 2026-01-15 | 2026-02-09 | 01 FIRST - FINISH FLOOR > E-124 |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33
#1692 | Coordination of Basic Roof | In dispute | Safety | Safety Infraction |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-10-30 14:26 | 2026-01-15 | 2026-02-09 |  |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33
#1691 | COI | In dispute | Safety | Safety Infraction |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-10-30 11:44 | 2026-01-15 | 2026-02-09 |  |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33
#1690 | Quality | In dispute | Safety | Safety Infraction |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-10-29 15:38 | 2026-01-15 | 2026-02-09 |  |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33
#1689 | Internal T&M | Draft | Concrete Crew | Safety |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-10-29 15:38 | 2026-01-15 | 2026-02-09 |  |  |  | Human - Human error | Published |  | 2026-02-19 02:24
#1688 | Coordination of Floor | In dispute | Safety | Safety Infraction |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-10-29 13:47 | 2026-01-15 | 2026-02-09 |  |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33
#1685 | Mechanical Equipment CX | In dispute | Safety | Safety Infraction |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-10-28 13:33 | 2026-01-15 | 2026-02-09 | 01 FIRST - FINISH FLOOR > E-124 |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33
#1684 | Finish | In progress | Concrete Crew | Finish |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-10-24 07:24 | 2026-04-23 | [5 empty] | Published |  | 2026-04-20 02:52
#1683 | Safety | In dispute | Safety | Safety Infraction |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-10-23 14:54 | 2026-01-15 |  |  |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33
#1682 | Inspection | Open | Concrete Crew | Inspection |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-10-23 14:23 | 2026-04-23 |  | 01 FIRST - FINISH FLOOR > E-125 |  |  |  | Published |  | 2026-04-20 02:52
#1681 | COI | Closed | Admin Insurance | COI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-10-22 14:23 | 2026-04-20 | [5 empty] | Published |  | 2026-04-17 05:27 | Mark Mergenschroer Owners Inc | 2025-11-03 14:58
#1679 | COI | Open | Admin Insurance | COI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-10-21 19:20 | 2026-04-20 | [5 empty] | Published |  | 2026-04-17 05:27
#1678 | COI | Open | Admin Insurance | COI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-10-21 19:20 | 2026-04-20 | [5 empty] | Published |  | 2026-04-17 05:27
#1677 | COI | Open | Admin Insurance | COI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-10-21 19:20 | 2026-04-20 | [5 empty] | Published |  | 2026-04-17 05:27
#1676 | COI | Open | Admin Insurance | COI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-10-21 18:59 | 2026-04-20 | [5 empty] | Published |  | 2026-04-17 05:27
#1675 | Commissioning | Closed | Commissioning | Commissioning |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-10-14 14:21 | 2026-04-20 | [5 empty] | Published |  | 2026-04-17 05:27 | Soroor Zamani ACS-TSE-Construction | 2025-10-14 21:25
#1674 | Architectural Punch List | Draft | Punch List | Architectural Punch List |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-10-14 08:01 | 2026-04-20 |  | 05 ROOF |  |  |  | Published |  | 2026-04-17 05:27
#1673 | Punch List | Draft | Punch List | Architectural Punch List | This is the template text | Autodesk | Autodesk | Autodesk | Autodesk | 2025-10-14 07:55 | 2026-04-20 |  | 00 FIRST - FINISH FLOOR |  |  |  | Published |  | 2026-04-17 05:27
#1672 | Steel Bid | Open | Fabrication | Steel Bid |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-10-10 11:02 | 2025-10-17 | [5 empty] | Published |  | 2025-10-10 11:03
#1670 | Subcontractor T&M- | Draft | Observation | Safety |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-10-09 06:11 | 2026-04-23 | [5 empty] | Published |  | 2026-04-20 02:52
#1669 | Finish | Open | Concrete Crew | Finish | Incorrect material. Reference specs. | Autodesk | Autodesk | Autodesk | Autodesk | 2025-10-08 10:29 | 2025-10-10 | 2025-10-08 | 04 FOURTH - FINISH FLOOR |  |  | Material - Wrong material | Published |  | 2025-10-08 10:32
#1668 | New Issue fgound - needs to be fxied | Open | Admin Insurance | COI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-10-08 06:30 | 2026-04-20 | [5 empty] | Published |  | 2026-04-17 05:27
#1667 | Architectural Punch List | Draft | Punch List | Architectural Punch List |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-10-07 13:23 | 2026-04-20 | [5 empty] | Published |  | 2026-04-17 05:27
#1666 | COI | Open | Admin Insurance | COI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-10-07 12:58 | 2026-04-20 | [5 empty] | Published |  | 2026-04-17 05:27
#1665 | Coordination | Open | Coordination | Coordination | Ceiling condition coordination issue, please advise | Autodesk | Autodesk | Autodesk | Autodesk | 2025-10-07 12:40 | 2026-04-20 | [5 empty] | Published |  | 2026-04-17 05:27
#1664 | Mechanical Equipment CX | Open | Commissioning | Mechanical Equipment CX |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-10-06 08:15 | 2026-04-23 | [5 empty] | Published |  | 2026-05-13 12:04
#1663 | Punch List | Open | Punch List | Punch List |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-10-01 13:07 | 2026-04-23 | [5 empty] | Published |  | 2026-04-20 02:52
#1662 | Punch List | Open | Punch List | Punch List |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-10-01 11:22 | 2026-04-23 | [5 empty] | Published |  | 2026-04-20 02:52
#1661 | Punch List | Open | Punch List | Punch List |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-10-01 10:55 | 2026-04-23 | [5 empty] | Published |  | 2026-04-20 02:52
#1660 | Fall Risk | In dispute | Safety | Safety Infraction | East ledge of second floor elevator shaft not roped off sufficiently | Autodesk | Autodesk | Autodesk | Autodesk | 2025-09-25 07:55 | 2025-09-26 | 2025-09-25 | 02 SECOND - FINISH FLOOR |  |  | Inadequate Training | Published |  | 2026-02-19 02:33
#1659 | Quality | Open | Concrete Crew | Quality |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-09-24 06:44 | 2026-04-23 | [5 empty] | Published |  | 2026-04-20 02:52
#1658 | Punch List | Open | Punch List | Punch List |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-09-22 09:51 | 2026-04-23 |  | 01 FIRST - FINISH FLOOR > E-102 |  |  |  | Published |  | 2026-04-20 02:52
#1657 | Commissioning | Open | Commissioning | Commissioning |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-09-19 09:03 | 2026-04-20 |  | 00 BASEMENT |  |  |  | Published |  | 2026-04-17 05:27
#1656 | Punch List | Open | Punch List | Punch List |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-09-19 08:23 | 2026-04-23 | [5 empty] | Published |  | 2026-04-20 02:52
#1655 | Punch List | Open | Punch List | Punch List |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-09-19 08:23 | 2026-04-23 | [5 empty] | Published |  | 2026-04-20 02:52
#1654 | Delivered with damage | Open | Design | Design | Box was damaged. No signature at delivery. | Autodesk | Autodesk | Autodesk | Autodesk | 2025-09-19 08:21 | 2026-04-23 | [5 empty] | Published |  | 2026-04-20 02:52
#1651 | Design Review | Open | Design | Design |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-09-16 06:36 | 2025-12-18 | [5 empty] | Published |  | 2025-12-15 11:56
#1650 | Drywall Progress Delays | Open | Concrete Crew | Finish |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-09-11 06:47 | 2026-04-23 | [5 empty] | Published |  | 2026-04-20 02:52
#1649 | Carpet Punch List | Open | Observation | Quality |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-09-11 06:43 | 2025-09-13 |  |  |  |  | Inadequate Training | Published |  | 2026-02-19 02:27
#1647 | design | Open | Admin Insurance | COI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-09-09 09:38 | 2026-04-20 | [5 empty] | Published |  | 2026-04-17 05:27
#1646 | Owners Issues | Open | Design | Design |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-09-04 07:39 | 2025-09-09 | [5 empty] | Published |  | 2025-09-04 07:41 |  |  | Ali Atabey (Sep 4, 2025, 7:40 AM PDT): @Cheryle Cranbourne where are we in the process of this issue? Cheryle Cranbourne (Sep 4, 2025, 7:40 AM PDT): Almost complete
#1645 | Inspection | Open | Concrete Crew | Inspection | Issue | Autodesk | Autodesk | Autodesk | Autodesk | 2025-09-03 12:14 | 2026-04-23 |  | 03 THIRD - FINISH FLOOR > E-325 |  |  |  | Published |  | 2026-04-20 02:52
#1644 | Potholing - Gas Line | Open | Earthwork | Potholing - Gas Line |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-08-28 11:28 | 2026-04-23 | [5 empty] | Published |  | 2026-04-20 02:52
#1643 | Pot Holing | Open | Concrete Crew | Inspection | Potholed on 8/28/25 Encountered unforeseen utility line from AT&T. | Autodesk | Autodesk | Autodesk | Autodesk | 2025-08-28 11:16 | 2025-09-18 | 2025-08-28 |  |  |  |  | Published |  | 2025-08-28 11:20
#1642 | Punch List | Open | Punch List | Punch List |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-08-28 10:52 | 2026-04-23 | [5 empty] | Published |  | 2026-04-20 02:52
#1640 | Faulty Outlet | Draft | Punch List | Architectural Punch List | This is the template text | Autodesk | Autodesk | Autodesk | Autodesk | 2025-08-27 11:21 | 2026-04-20 | [5 empty] | Published |  | 2026-04-17 05:27 |  |  | Matt Bunis (Aug 27, 2025, 11:22 AM PDT): @Matt Bunis we need an answer ASAP
#1639 | Coordination of Footing-Rectangular | Draft | Concrete Crew | Design Conflict |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-08-26 12:28 | 2026-04-23 | [5 empty] | Published |  | 2026-04-20 02:52
#1638 | Design Conflict | Not approved | Safety | Safety Infraction |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-08-26 11:31 | 2026-04-23 |  | 02 SECOND - FINISH FLOOR > W-222 |  |  | Equipment - Improper equipment | Unpublished |  | 2026-06-16 11:38 |  |  | Neil Rosado (Aug 26, 2025, 11:32 AM PDT): @Buddy Legnon please chat with Luke for resolution Cheryle Cranbourne (Jan 15, 2026, 11:29 AM PST): Spoke to Luke -- we're all set Soroor Zamani (Jun 16, 2026, 11:37 AM PDT): @Luke Hester FYI
#1637 | Internal T&M | In progress | Observation | Safety |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-08-20 08:58 | 2026-04-23 | [5 empty] | Published |  | 2026-04-20 02:52
#1636 | Contractor Punch List | In progress | Punch List | Contractor Punch List |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-08-14 13:04 | 2026-04-20 |  | 01 FIRST - FINISH FLOOR > E-145 |  |  |  | Published |  | 2026-04-17 05:27
#1635 | Punch List | In progress | Punch List | Punch List |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-08-14 11:50 | 2026-04-23 | [5 empty] | Published |  | 2026-04-20 02:52
#1634 | Punch List | Draft | Punch List | Architectural Punch List | This is the template text | Autodesk | Autodesk | Autodesk | Autodesk | 2025-08-14 11:35 | 2026-04-20 | [5 empty] | Published |  | 2026-04-17 05:27 |  |  | Matt Bunis (Sep 8, 2025, 1:33 PM PDT): @Matt Bunis hey we need an answer on this ASAP
#1633 | Quality | Open | Quality | Quality |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-08-14 08:31 | 2026-04-23 | [5 empty] | Published |  | 2026-04-20 02:52
#1631 | Contractor Punch List | Completed | Punch List | Contractor Punch List |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-08-05 13:27 | 2026-04-20 |  | 01 FIRST - FINISH FLOOR > E-102 |  |  |  | Published |  | 2026-04-17 05:27
#1630 | Mechanical Design Conflict | In review | Concrete Crew | Design Conflict | test | Autodesk | Autodesk | Autodesk | Autodesk | 2025-08-05 07:41 | 2025-08-15 |  | 03 THIRD - FINISH FLOOR |  |  | Design Coordination | Published |  | 2025-08-05 07:41
#1629 | Punch List | Open | Punch List | Punch List |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-08-05 07:19 | 2026-04-23 | [5 empty] | Published |  | 2026-04-20 02:52
#1628 | Design Conflict | Draft | Concrete Crew | Design Conflict |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-08-04 13:14 | 2026-04-23 | [5 empty] | Published |  | 2026-04-20 02:52
#1627 | Design Conflict | Draft | Concrete Crew | Design Conflict |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-08-04 11:24 | 2026-04-23 | [5 empty] | Published |  | 2026-04-20 02:52
#1626 | Punch List | Open | Punch List | Punch List |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-08-04 10:22 | 2026-04-23 | [5 empty] | Published |  | 2026-04-20 02:52 |  |  | Matt Bunis (Aug 5, 2025, 7:27 AM PDT): @Matt Bunis hey i need this turned around ASAP
#1625 | Small Works Handoff | Open | Commissioning | Small Works Handoff |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-08-04 08:57 | 2026-04-23 | [5 empty] | Published |  | 2026-04-20 02:52 | [30 empty] | 6 months | 1382764187
#1624 | Architectural Punch List | Draft | Punch List | Architectural Punch List |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-08-04 08:53 | 2026-04-20 | [5 empty] | Published |  | 2026-04-17 05:27
#1623 | Owner T&M Directive | In dispute | Observation | Safety | Change Patio sets for Halloween Decoration | Autodesk | Autodesk | Autodesk | Autodesk | 2025-07-31 11:19 | 2026-04-23 | [5 empty] | Published |  | 2026-04-20 02:52
#1622 | Contractor Punch List | Open | Punch List | Contractor Punch List |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-07-31 08:26 | 2026-04-20 | [5 empty] | Published |  | 2026-04-17 05:27
#1621 | Architectural Punch List | Draft | Punch List | Architectural Punch List |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-07-30 14:34 | 2026-04-20 | [5 empty] | Published |  | 2026-04-17 05:27
#1620 | Punch List | Pending | Punch List | Punch List |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-07-30 12:57 | 2026-04-23 |  | 01 FIRST - FINISH FLOOR > E-106 |  |  |  | Published |  | 2026-04-20 02:52
#1619 | Misc | Closed | Concrete Crew | Misc |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-07-30 12:50 | 2026-04-23 |  | 01 FIRST - FINISH FLOOR > E-124 |  |  |  | Published |  | 2026-04-20 02:52 | John Tymkowicz Autodesk | 2025-10-14 15:22
#1618 | Punch List | Open | Punch List | Punch List |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-07-29 12:39 | 2026-04-23 | [5 empty] | Published |  | 2026-05-04 13:05 |  |  | Luke Hester (Jul 30, 2025, 8:48 AM PDT): @Luke Hester notifications service test | Add comments here
#1617 | Clash | Open | Coordination | Clash |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-07-25 11:22 | 2026-04-20 | [5 empty] | Published |  | 2026-04-17 05:27
#1616 | Contractor Punch List | Closed | Punch List | Contractor Punch List |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-07-23 14:15 | 2026-04-20 |  | 01 FIRST - FINISH FLOOR > E-145 |  |  |  | Published |  | 2026-04-17 05:27 | Mark Mergenschroer Owners Inc | 2025-11-03 14:58
#1615 | COI | Open | Admin Insurance | COI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-07-23 13:10 | 2026-04-20 | [5 empty] | Published |  | 2026-04-17 05:27
#1614 | Internal T&M | Draft | Observation | Safety |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-07-23 12:30 | 2026-04-23 | [5 empty] | Published |  | 2026-04-20 02:52
#1613 | Quality | Open | Concrete Crew | Quality |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-07-23 12:19 | 2026-04-23 | [5 empty] | Published |  | 2026-04-20 02:52 |  |  | Matt Bunis (Aug 14, 2025, 11:46 AM PDT): @Matt Bunis need your thoughts on this
#1612 | COI | Open | Admin Insurance | COI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-07-22 06:37 | 2026-04-20 |  | 01 FIRST - FINISH FLOOR > E-101 |  |  |  | Published |  | 2026-04-17 05:27
#1611 | RFI | Open | Commissioning | RFI |  | Autodesk | Autodesk | Autodesk | Autodesk | 2025-07-17 07:26 | 2026-04-23 | [5 empty] | Published |  | 2026-04-20 02:52 | [9 empty] | YES
#1583 | Design Conflict | Draft | Safety | Safety Infraction | Crack concrete, please course correct. | Autodesk | Autodesk | Autodesk | Autodesk | 2025-06-10 10:28 | 2025-06-24 | 2025-06-10 |  |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:30
#1582 | Architectural Punch List | Completed | Punch List | Architectural Punch List | Rubber base is not adhering to the walls. | Autodesk | Autodesk | Autodesk | Autodesk | 2025-06-06 12:35 | 2026-04-20 |  | 01 FIRST - FINISH FLOOR > E-125 |  |  |  | Published |  | 2026-04-17 05:27 | Lisa Chen | 2025-06-27 15:24 | Lisa Chen (Jun 27, 2025, 8:25 AM PDT): @Danielle Guieb Punchlist not approved. The subcontractor didn't do the fix properly.
#1580 | BOMEL PL Paint | Closed | Safety | Safety Infraction | This is the template text | Autodesk | Autodesk | Autodesk | Autodesk | 2025-06-05 09:14 | 2025-06-06 |  | 04 FOURTH - FINISH FLOOR |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:30 | John Tymkowicz Autodesk | 2025-10-14 15:20 | Soroor Zamani (Jun 5, 2025, 9:14 AM PDT): @Gabe Morales This is Done!
#1577 | Design Conflict - Wall length too short | Draft | Concrete Crew | Finish | Please check requirements | Autodesk | Autodesk | Autodesk | Autodesk | 2025-05-29 10:43 | 2025-06-12 | [5 empty] | Published |  | 2025-05-29 10:45
#1569 | Quality | Open | Concrete Crew | Quality | There is concrete spalling, please fix due to punchlist items. | Autodesk | Autodesk | Autodesk | Autodesk | 2025-05-20 12:20 | 2025-06-17 | 2025-05-20 | SUBSTRUCTURE |  |  |  | Published |  | 2025-05-20 12:21
#1568 | Quality | Open | Concrete Crew | Quality | The Curtain wall is cracked. | Autodesk | Autodesk | Autodesk | Autodesk | 2025-05-19 12:54 | 2025-06-13 | 2025-05-19 |  |  |  |  | Published |  | 2025-05-19 12:55
#1566 | Quality | Open | Concrete Crew | Quality | Spalling in concrete. | Autodesk | Autodesk | Autodesk | Autodesk | 2025-05-14 11:10 | 2025-05-30 | 2025-05-14 |  |  |  |  | Published |  | 2025-12-18 08:39 |  |  | Lisa Chen (May 14, 2025, 11:12 AM PDT): @Alyssa Schear please take a look at this before the end of the week with the Architect.
#1557 | Subcontractor T&M | Draft | Observation | Safety | Unforeseen underground AT&T lines. | Autodesk | Autodesk | Autodesk | Autodesk | 2025-05-08 09:54 | 2025-05-22 | 2025-05-08 |  |  |  |  | Published |  | 2026-02-18 14:49 |  |  | Lisa Chen (May 8, 2025, 9:58 AM PDT): @Alex van Hoff Hey let's get together to review this matter.
#1548 | Needs to change for RFI | Closed | Safety | Safety Infraction | Please update wall type | Autodesk | Autodesk | Autodesk | Autodesk | 2025-05-01 10:31 | 2025-05-05 |  | 05 ROOF |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:30 | Ali Atabey Autodesk | 2025-05-01 17:34 | Ali Atabey (May 1, 2025, 10:33 AM PDT): Does this need to be fire rated?
#1541 | Design Conflict | Draft | Observation | Safety | Scaffolding design conflict, please advise. | Autodesk | Autodesk | Autodesk | Autodesk | 2025-04-17 11:15 | 2025-05-08 | 2025-04-17 |  |  |  | Design Deficiency | Published |  | 2026-07-17 09:33 |  |  | Lisa Chen (Apr 17, 2025, 11:17 AM PDT): @Marcus Butler Could you please review this scaffolding design by the end of the day for tomorrow's work?
#1537 | Owners Issues | Open | Design | Design | Door is on the wrong side | Autodesk | Autodesk | Autodesk | Autodesk | 2025-04-10 09:28 | 2025-04-15 |  | 01 FIRST - FINISH FLOOR > E-129 |  |  |  | Published |  | 2025-04-10 09:34 |  |  | Wes Newman (Apr 10, 2025, 9:32 AM PDT): Is it on the wrong wall or on the wrong side of the wall it's on? Michael Bugbee (Apr 10, 2025, 9:33 AM PDT): @Wes Newman Please fix the location of the door, it needs to be on the north side of the room. Wes Newman (Apr 10, 2025, 9:33 AM PDT): @Michael Bugbee Got it!
#1534 | Inspection | Open | Concrete Crew | Inspection | Fix the base plate | Autodesk | Autodesk | Autodesk | Autodesk | 2025-04-09 07:29 | 2025-04-11 |  | New Area |  |  | Engineering Bust | Published |  | 2025-04-09 07:36
#1509 | Check Window Sash Lock Mechanism | Completed | Quality | Quality | Window Sash Lock Mechanism is not as per specs | Autodesk | Autodesk | Autodesk | Autodesk | 2025-02-21 06:07 | 2026-05-12 | [5 empty] | Published |  | 2026-05-12 03:16
#1503 | Patch and Repair Drywall | Draft | Safety | Safety Infraction | Sand this section again | Autodesk | Autodesk | Autodesk | Autodesk | 2025-02-04 09:33 | 2025-02-05 |  | 01 FIRST - FINISH FLOOR > E-123 |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:30
#1474 | Punch List | In dispute | Safety | Safety Infraction | Missing cornerguard. | Autodesk | Autodesk | Autodesk | Autodesk | 2025-01-15 12:38 | 2025-01-29 | 2025-01-15 | 00 FIRST - FINISH FLOOR > W-110 |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33
#1464 | Safety | In dispute | Safety | Safety Infraction | Unforeseen AT&T lines. | Autodesk | Autodesk | Autodesk | Autodesk | 2024-12-19 11:43 | 2025-01-23 | 2025-01-16 | 00 FIRST - FINISH FLOOR |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33
#1456 | Quality | In dispute | Safety | Safety Infraction | Concrete is spalling on this panel. Let's review the concrete design mix. | Autodesk | Autodesk | Autodesk | Autodesk | 2024-12-17 12:21 | 2025-01-14 | 2024-12-17 | 01 FIRST - FINISH FLOOR |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33
#1442 | Punch List TV Clearance and Height | Open | Punch List | Architectural Punch List | Please check clearance and height, electrical requirements for this location | Autodesk | Autodesk | Autodesk | Autodesk | 2024-12-06 08:02 | 2026-04-20 | 2024-12-06 | 01 FIRST - FINISH FLOOR > E-106 | FIrst Floor lobby east wall |  | Owner Change | Published |  | 2026-04-17 05:27 | John Tymkowicz Autodesk | 2025-10-14 15:20 |  |  | Cost
#1439 | Patch and Repair Drywall | Closed | Safety | Safety Infraction | Sand this section again | Autodesk | Autodesk | Autodesk | Autodesk | 2024-12-03 07:24 | 2024-12-27 | 2024-11-25 | 01 FIRST - FINISH FLOOR > E-124 |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:30 | John Tymkowicz Autodesk | 2025-10-14 15:20
#1437 | Observation | In dispute | Safety | Safety Infraction | Is Game Room E-237 to be added to the Subcontractor's scope of work? | Autodesk | Autodesk | Autodesk | Autodesk | 2024-11-26 07:38 | 2024-12-12 | 2024-12-03 |  |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33
#1436 | Inspection | Open | Concrete Crew | Inspection | Incinerator is installed in the wrong location. | Autodesk | Autodesk | Autodesk | Autodesk | 2024-11-26 06:18 | 2024-12-20 | 2024-11-26 | 05 ROOF |  |  |  | Published |  | 2026-04-15 12:52 |  |  | Lisa Chen (Nov 26, 2024, 6:19 AM PST): @Alyssa Schear Please review this issue before the EOD.
#1430 | Patch and Repair Drywall | In dispute | Safety | Safety Infraction | Sand this section again | Autodesk | Autodesk | Autodesk | Autodesk | 2024-11-15 10:48 | 2024-11-19 | 2024-11-06 | 03 THIRD - FINISH FLOOR > E-326 |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33
#1426 | General | Not approved | General | General | VE option | Autodesk | Autodesk | Autodesk | Autodesk | 2024-11-13 10:41 | 2024-12-10 | 2024-11-19 |  |  |  |  | Published |  | 2026-05-04 07:09
#1422 | Punch List | Open | Punch List | Punch List | Concrete spalling in the fascade. | Autodesk | Autodesk | Autodesk | Autodesk | 2024-11-11 11:44 | 2024-11-25 | 2024-11-11 |  |  |  |  | Published |  | 2024-11-11 11:46 |  |  | Lisa Chen (Nov 11, 2024, 11:45 AM PST): @Ondrei Poliak I need this by the end of the day.
#1421 | Punch List | Open | Punch List | Punch List | Door Jamb failed. | Autodesk | Autodesk | Autodesk | Autodesk | 2024-11-11 09:41 | 2024-11-25 | 2024-11-11 |  |  |  |  | Published |  | 2024-11-11 09:43
#1417 | Punch List | Open | Punch List | Punch List | Replace man hole cover. | Autodesk | Autodesk | Autodesk | Autodesk | 2024-11-07 09:13 | 2024-11-19 | 2024-11-07 |  |  |  |  | Published |  | 2024-11-07 09:48
#1407 | Owners Issues | Not approved | Concrete Crew | Inspection | Owners Issues | Autodesk | Autodesk | Autodesk | Autodesk | 2024-10-28 08:37 | 2024-11-02 |  | 05 ROOF |  |  |  | Published |  | 2024-10-29 17:15
#1393 | Punch List | Open | Punch List | Punch List | trade damage | Autodesk | Autodesk | Autodesk | Autodesk | 2024-10-22 09:39 | 2024-10-29 | 2024-10-22 | 02 SECOND - FINISH FLOOR > W-224 |  |  |  | Published |  | 2024-10-22 09:40
#1392 | Patch and Repair Drywall | In dispute | Safety | Safety Infraction | Sand this section again | Autodesk | Autodesk | Autodesk | Autodesk | 2024-10-21 11:58 | 2026-05-20 |  | 04 FOURTH - FINISH FLOOR |  |  | Equipment - Improper equipment | Published |  | 2026-05-14 08:36 |  |  | John Tymkowicz (Oct 8, 2025, 10:44 AM PDT): What's the status of this? @AE Architects
#1387 | Punch List | Completed | Punch List | Punch List | Patch drywall | Autodesk | Autodesk | Autodesk | Autodesk | 2024-10-14 11:21 | 2024-10-28 | 2024-10-14 | 04 FOURTH - FINISH FLOOR > E-411 | West facing interior wall |  | Trade Damage | Published |  | 2024-11-08 11:45
#1371 | Mechanical Design Conflict | Open | Concrete Crew | Design Conflict | Test | Autodesk | Autodesk | Autodesk | Autodesk | 2024-09-26 13:13 | 2024-10-06 |  | 05 ROOF |  |  | Design Coordination | Published |  | 2024-10-01 12:35
#1370 | Client Feedback | Completed | Safety | Safety Infraction | Don't like this. Move the column | Autodesk | Autodesk | Autodesk | Autodesk | 2024-09-23 11:37 | 2024-09-26 |  | 03 THIRD - FINISH FLOOR |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:30
#1369 | Design | Open | Design | Design | Change handrail type | Autodesk | Autodesk | Autodesk | Autodesk | 2024-09-20 09:33 | 2024-09-27 | 2024-09-20 |  |  |  |  | Published |  | 2024-09-20 09:34
#1365 | Obs | In dispute | Safety | Safety Infraction | VE option | Autodesk | Autodesk | Autodesk | Autodesk | 2024-09-17 09:45 | 2024-09-24 | 2024-09-17 |  |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33
#1364 | Changing Concrete Stairs to Structural Steel Stairs | Open | Design | Design | Structural Steel Stairs | Autodesk | Autodesk | Autodesk | Autodesk | 2024-09-13 10:58 | 2024-09-18 | 2024-09-27 |  |  |  |  | Published |  | 2024-09-13 10:58
#1363 | Trench Drain Damage Post-Install | Open | Concrete Crew | Quality | Please see attached photo - resolve by EOD on Friday 10/11 | Autodesk | Autodesk | Autodesk | Autodesk | 2024-09-12 08:24 | 2024-10-10 |  | 01 FIRST - FINISH FLOOR > E-113 |  |  |  | Published |  | 2025-04-03 05:26
#1362 | Design Conflict | Open | Concrete Crew | Quality | Formwork is 2" wider than the drawings show | Autodesk | Autodesk | Autodesk | Autodesk | 2024-09-12 08:17 | 2024-09-16 |  | SUBSTRUCTURE |  |  | Poor Construction | Published |  | 2024-10-09 07:51
#1348 | Floor [8874781] and 12 other objects. | Open | Concrete Crew | Inspection | 12 clashes between Floor [8874781] in 5190_JHUHSC_ARSB_ENVELOPE_R22.rvt - {3D} and 5190_JHUHSC_ARSB_MAIN_R22.rvt - {3D} | Autodesk | Autodesk | Autodesk | Autodesk | 2024-09-03 10:32 | 2024-09-19 | 2024-09-19 |  |  |  |  | Published |  | 2024-09-03 10:32
#1347 | Basic Wall [1001450] and Rectangular Duct [2526105] | Open | Coordination | Clash | 1 clash between Basic Wall [1001450] in R21 LTU Housing - Arch.rvt - {3D - neetha.puthran} and R21 LTU Housing - MECHANICAL.rvt - MEP - COORDINATION | Autodesk | Autodesk | Autodesk | Autodesk | 2024-08-29 07:46 | 2026-04-20 | [5 empty] | Published |  | 2026-04-17 05:27 |  |  | Ali Atabey (Aug 29, 2024, 7:46 AM PDT): @AP Percowycz please review ASAP
#1336 | Quality | In dispute | Safety | Safety Infraction | Metal Wall Panel waterproofing issue. | Autodesk | Autodesk | Autodesk | Autodesk | 2024-08-16 08:52 | 2024-08-30 | 2024-08-16 | 01 FIRST - FINISH FLOOR |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33
#1327 | Mechanical Equipment CX | Open | Commissioning | Mechanical Equipment CX | Replace AU unit | Autodesk | Autodesk | Autodesk | Autodesk | 2024-08-08 08:26 | 2024-08-30 | 2024-08-08 | 05 ROOF | GL-A1 |  |  | Published |  | 2024-08-08 08:29
#1303 | Electric Panel Repair | Closed | XL Safety | Incident | Electrical Panel blew up. Needs replacement. | Autodesk | Autodesk | Autodesk | Autodesk | 2024-07-17 11:10 | 2024-10-08 |  | 01 FIRST - FINISH FLOOR > E-125 |  |  |  | Published |  | 2025-07-17 11:00 | Austin Ehlert ACS-TSE-Construction | 2025-07-17 18:00
#1285 | General | In dispute | Safety | Safety Infraction | PPE | Autodesk | Autodesk | Autodesk | Autodesk | 2024-06-25 10:41 | 2024-06-28 |  | SUBSTRUCTURE > ZONE 2 |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33
#1281 | Safety | In dispute | Observation | Safety | Debris in stairwell | Autodesk | Autodesk | Autodesk | Autodesk | 2024-06-20 09:22 | 2024-06-27 |  | 01 FIRST - FINISH FLOOR > E-129 |  |  |  | Published |  | 2024-06-28 10:27
#1262 | G-test001 | Open | Punch List | Architectural Punch List | This is the template text | Autodesk | Autodesk | Autodesk | Autodesk | 2024-06-06 09:52 | 2026-04-20 | 2024-06-06 | 04 FOURTH - FINISH FLOOR > W-421 |  |  | Design Deficiency | Published |  | 2026-04-17 05:27 |  |  | Neil Rosado (Jun 6, 2024, 9:53 AM PDT): @Luke Hester please verify Neil Rosado (Jun 6, 2024, 9:56 AM PDT): not approved based on ...
#1255 | Patch and Repair Drywall | In dispute | Safety | Safety Infraction | Sand this section again | Autodesk | Autodesk | Autodesk | Autodesk | 2024-05-20 13:55 | 2024-06-07 |  | 02 SECOND - FINISH FLOOR |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33
#1193 | Inspection | In dispute | Safety | Safety Infraction | Is this plaster surface EFIS? | Autodesk | Autodesk | Autodesk | Autodesk | 2024-02-22 09:48 | 2024-03-14 | 2024-02-22 | 00 FIRST - FINISH FLOOR |  |  | Equipment - Improper equipment | Published |  | 2026-02-20 12:39 |  |  | Lisa Chen (Feb 22, 2024, 9:48 AM PST): @Austin Ehlert I need this reviewed by the end of today, would you be able to sign off? Luke Hester (Feb 20, 2026, 12:39 PM PST): @Ali Atabey
#1187 | Coordination | Open | Coordination | Coordination | Existing Condition | Autodesk | Autodesk | Autodesk | Autodesk | 2024-02-21 07:49 | 2026-04-20 | 2024-02-21 | 01 FIRST - FINISH FLOOR |  |  |  | Published |  | 2026-04-17 05:27 |  |  | Ian Coats (Feb 21, 2024, 7:51 AM PST): Random Comment here
#1186 | Need toe kick for storefront | In dispute | Safety | Safety Infraction | for cost purposes we need a toe kick with tempered glass | Autodesk | Autodesk | Autodesk | Autodesk | 2024-02-20 07:39 | 2024-03-12 |  |  |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33 |  |  | Ali Atabey (Feb 20, 2024, 7:45 AM PST): @Alyssa Schear can you confirm the code?
#1165 | Punch List | Closed | Punch List | Architectural Punch List | This is the template text | Autodesk | Autodesk | Autodesk | Autodesk | 2024-01-31 09:28 | 2026-04-20 |  | 03 THIRD - FINISH FLOOR |  |  | Impact Damage | Published |  | 2026-04-17 05:27 | Helina Gebru Autodesk | 2024-01-31 17:34
#1163 | Observation | Open | Observation | Observation | Sample | Autodesk | Autodesk | Autodesk | Autodesk | 2024-01-31 08:21 | 2024-02-09 | 2024-01-31 | 01 FIRST - FINISH FLOOR |  |  |  | Published |  | 2024-01-31 08:23
#1161 | Clash | Open | Coordination | Clash | sample | Autodesk | Autodesk | Autodesk | Autodesk | 2024-01-30 09:07 | 2026-04-20 |  |  |  |  | Management - Lack of procedure | Published |  | 2026-04-17 05:27
#1160 | Inspection | In progress | Observation | Safety | Concrete has issues, spalling. Checking concrete mix, correct PSI? | Autodesk | Autodesk | Autodesk | Autodesk | 2024-01-30 08:41 | 2024-02-16 | 2024-01-30 |  |  |  | Constructability | Published |  | 2026-02-19 02:27 |  |  | Lisa Chen (Jan 30, 2024, 8:43 AM PST): @Samuel Spears send file to Esteban to review this concrete mix in the submittals.
#1155 | Punch List | Not approved | Punch List | Punch List | HVAC location | Autodesk | Autodesk | Autodesk | Autodesk | 2024-01-26 13:08 | 2024-02-02 | 2024-01-26 | 00 FIRST - FINISH FLOOR |  |  | Coordination | Published |  | 2024-05-03 07:19
#1136 | Inspection | Open | Concrete Crew | Inspection | Window is broken, needs replacing before substantial completion. | Autodesk | Autodesk | Autodesk | Autodesk | 2023-12-20 09:18 | 2024-01-17 | 2023-12-20 |  |  |  | Construction Defects | Published |  | 2023-12-20 09:20 |  |  | Lisa Chen (Dec 20, 2023, 9:19 AM PST): @Alyssa Schear
#1134 | Design Conflict | Draft | Concrete Crew | Design Conflict | Replace with polished concrete flooring. | Autodesk | Autodesk | Autodesk | Autodesk | 2023-12-18 10:53 | 2024-01-08 | 2023-12-18 |  |  |  |  | Published |  | 2023-12-19 15:31 |  |  | Lisa Chen (Dec 18, 2023, 10:54 AM PST): @Jack Hopson Hey Jack, please review this issue by the EOD and communicate to the team.
#1133 | Inspection | In dispute | Safety | Safety Infraction | Plaster is peeling on the exterior. | Autodesk | Autodesk | Autodesk | Autodesk | 2023-12-14 14:51 | 2023-12-28 | 2023-12-14 | 02 SECOND - FINISH FLOOR > W-224 |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33
#1132 | Quality | In dispute | Safety | Safety Infraction | Start up texting incomplete | Autodesk | Autodesk | Autodesk | Autodesk | 2023-12-14 14:41 | 2023-12-19 |  |  |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33
#1123 | Quality | Open | Concrete Crew | Quality | Door Hinge needs to be replaced. | Autodesk | Autodesk | Autodesk | Autodesk | 2023-12-08 12:22 | 2023-12-11 | 2023-12-08 | 03 THIRD - FINISH FLOOR > W-318 |  |  |  | Published |  | 2023-12-08 12:24 |  |  | Lisa Chen (Dec 8, 2023, 12:23 PM PST): @Carl Clad I really need this door by the End of Day tomorrow.
#1122 | Inspection | Pending | Installation | Rack Install | Installed panel 101 on 10/1. Inspection form attached. Electrical inspector scheduled on Thursday 10/10 | Autodesk | Autodesk | Autodesk | Autodesk | 2023-12-08 10:01 | 2024-10-10 | [5 empty] | Published |  | 2024-10-03 07:10 | Emmett Smith Autodesk | 2024-01-04 18:55 | Emmett Smith (Mar 6, 2024, 8:50 AM PST): @Austin Ehlert Please confirm inspector is arriving this morning Emmett Smith (Mar 25, 2024, 9:27 AM PDT): Inspector Ferguson confirmed this morning that he has us scheduled between 10-12 on Thursday
#1121 | COI | Open | Admin Insurance | COI | There is a delay. Is there a cost impact? Is there a schedule impact? | Autodesk | Autodesk | Autodesk | Autodesk | 2023-12-07 11:17 | 2026-04-20 | 2023-12-05 |  |  |  |  | Published |  | 2026-04-17 05:27
#1120 | Safety | In dispute | Safety | Safety Infraction | Unforseen duct bank in the way. | Autodesk | Autodesk | Autodesk | Autodesk | 2023-12-06 11:45 | 2026-01-15 | 2025-09-01 |  | Overlapping waterline at GL - 3 and GL - A |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33
#1112 | Punch List | Open | Punch List | Architectural Punch List | TEST FOR PERMISSIONS | Autodesk | Autodesk | Autodesk | Autodesk | 2023-11-29 07:20 | 2026-04-20 | [5 empty] | Published |  | 2026-04-17 05:27
#1111 | Inspection | In dispute | Safety | Safety Infraction | Concrete spalling happening. | Autodesk | Autodesk | Autodesk | Autodesk | 2023-11-28 15:46 | 2023-12-13 |  | SUBSTRUCTURE |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33
#1110 | Inspection | Open | Concrete Crew | Inspection | Painting punch item | Autodesk | Autodesk | Autodesk | Autodesk | 2023-11-28 09:49 | 2023-12-05 | [5 empty] | Published |  | 2023-11-28 09:49
#1099 | Residence 203 [1649846] and 11 other objects. | In dispute | Safety | Safety Infraction | 11 clashes between Residence 203 [1649846] in ADSK_Electrical.rvt - 3D - Just Electrical and ADSK_Plumbing.rvt - 3D Plumbing | Autodesk | Autodesk | Autodesk | Autodesk | 2023-11-02 09:59 | 2023-11-09 | 2023-11-02 |  | free text |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33 |  |  | Austin Ehlert (Nov 2, 2023, 10:00 AM PDT): @Austin Ehlert
#1086 | Inspection | Open | Concrete Crew | Inspection | The window is cracked upon final inspection walk through. | Autodesk | Autodesk | Autodesk | Autodesk | 2023-10-25 09:14 | 2023-11-16 | 2023-10-25 |  |  |  | Poor Construction | Published |  | 2024-11-12 12:32 |  |  | Lisa Chen (Oct 25, 2023, 9:15 AM PDT): @Buddy Legnon Hey Buddy, we this reviewed by EOD if possible for a first pass.
#1064 | Punch List | Open | Punch List | Architectural Punch List | Repair concrete spalling with concrete patching. | Autodesk | Autodesk | Autodesk | Autodesk | 2023-10-12 09:01 | 2026-04-20 | 2023-10-12 | SUBSTRUCTURE |  |  |  | Published |  | 2026-04-17 05:27
#1063 | Punch List | Open | Punch List | Architectural Punch List | Drywall damaged | Autodesk | Autodesk | Autodesk | Autodesk | 2023-10-12 07:14 | 2026-04-20 | 2023-10-12 | 03 THIRD - FINISH FLOOR | Conference Room Area |  | Impact Damage | Published |  | 2026-04-17 05:27
#1057 | Design Conflict | In dispute | Safety | Safety Infraction | Spandrel glass in not what we specified in specifications. | Autodesk | Autodesk | Autodesk | Autodesk | 2023-09-29 15:19 | 2023-10-26 | 2023-09-28 | 01 FIRST - FINISH FLOOR |  |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33 |  |  | Lisa Chen (Sep 29, 2023, 3:20 PM PDT): @Austin Ehlert Could please review this issue prior to the EOD?
#1053 | Punch List | In dispute | Safety | Safety Infraction | This is the template text | Autodesk | Autodesk | Autodesk | Autodesk | 2023-09-27 12:21 | 2023-09-14 |  | 05 ROOF | Roof north facing |  | Equipment - Improper equipment | Published |  | 2026-02-19 02:33
#1052 | Owner T&M Directive | In dispute | Observation | Safety | Owner wants different facade type | Autodesk | Autodesk | Autodesk | Autodesk | 2023-09-27 11:19 | 2023-10-19 | 2023-09-27 |  |  |  |  | Published |  | 2026-02-19 02:33 |  |  | Lisa Chen (Sep 27, 2023, 11:21 AM PDT): @AP Percowycz please address this underground unforeseen condition by the end of the week and review it with the team.
#1045 | Commissioning Example | Pending | Commissioning | Commissioning | Please include additional information for asset | Autodesk | Autodesk | Autodesk | Autodesk | 2023-09-20 06:54 | 2026-04-23 |  | 04 FOURTH - FINISH FLOOR > W-418 |  |  |  | Published |  | 2026-04-20 02:52 |  |  | Rachel Breed (Sep 20, 2023, 6:54 AM PDT): @Ali Atabey please add additional insight here | [28 empty] | 12345
#1041 | Quality | Open | Concrete Crew | Quality | The waterproofing is failing on the exterior. | Autodesk | Autodesk | Autodesk | Autodesk | 2023-09-08 12:18 | 2023-09-29 | 2023-09-08 |  |  |  | Design Deficiency | Published |  | 2023-09-08 12:20 |  |  | Lisa Chen (Sep 8, 2023, 12:20 PM PDT): @Nick Ramondo please review and comment.
#1036 | Design Conflict | Open | Concrete Crew | Design Conflict | Replace the glazing to storefront glazing instead of standard glazing. | Autodesk | Autodesk | Autodesk | Autodesk | 2023-09-05 11:41 | 2023-09-27 | 2023-09-05 | 00 FIRST - FINISH FLOOR > W-110 |  |  |  | Published |  | 2026-02-13 07:58
#1035 | Concrete Spalling on West Side | Open | Concrete Crew | Inspection | There is concrete spalling happening on the west side of the newly installed concrete panel. | Autodesk | Autodesk | Autodesk | Autodesk | 2023-09-05 11:04 | 2023-09-19 | 2023-09-05 | SUBSTRUCTURE | West Side of Building |  | Design Deficiency | Published |  | 2025-12-10 07:42 |  |  | Matt Bunis (Dec 10, 2025, 7:41 AM PST): @Miguel Coronel need you to jump on this ASAP